## Index
Bug Report For Noon APP
Reporter | Omar Abo Smrh
Title | Software Test Engineer
version | Android v1.0
Report To | Chefaa Company
Date | 2022-03-08
Reviewed By

## Bug Report_v1.0
ID | Module | TITLE | PRECONDITION | Test Data | STEPS | Actual Result | Expected Result | Severity | Priority | Attachement | Environment | Network | Assigned To | Status
Noon_001 | My Account | Miss Handling of click button meany times | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345706 | 1-open Noon app. 2-navigate to 'My Account'. 3- click on 'sign up' button meany times. | open meany form to sign up and sign up transfer to be clickable. | no reload or opening the sign up form. | Major | Hight | https://drive.google.com/file/d/1J32XxqiHbU3qx_ls6912ANK4FUuCgSR-/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_002 | All Modules | No Handling for internet connection interrupted | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345707 | 1-open Noon app. 2-navigate to any screen. 3- click on 'any' button . | app doesn't handling the missing of internet | popup message with connection status or no effect to the behavior of the app | Major | Medium | https://drive.google.com/file/d/1HgMCMN-MEwYhy27Ark_CU35n-Oqk6i0z/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_003 | سياسة الخصوصية' | the View of 'سياسة الخصوصية' not RTL(Right to Lift) | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345708 | 1-open Noon app. 2-navigate to arabic language. 3- Then navigate to' سياسة الخصوية' then click on it. | LTR | RTL | Minor | Low | https://drive.google.com/file/d/14afn0BXujBkEYw8jarMzucC4em3dugZ2/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_004 | Dynamic Links/ fb icon in footer | the app doesn't support deep/dynamic links | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345709 | 1-open noon app 2- navigate to share any product to facebook for example 3- try to re-open link! 4- or navigate to click on fb social media icon in footer. | doesn't support deep/dynamic links | the app should supporting deep/dynamic links | Moderate | Medium | https://drive.google.com/file/d/1fxFENUx1mge7B4S8_OEq_SQG1R3harEc/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_005 | My Account | Ahlan!' word should be 'Welcome!' | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345710 | 1-open Noon app. 2-navigate to login screen with english language. | Ahlan! | Welcome! | Cosmetic | Low | https://drive.google.com/file/d/1q8Ej-gvP17EhgzM9MkTlOmEFRXy622be/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_006 | Translation | miss translation of 'Free Delivery' to arabic | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345711 | 1-open Noon app. 2-navigate to products with arabic language. | Free Delivery by | should be "توصيل مجاني" | Minor | Low | https://drive.google.com/file/d/1dRqA2Vaj8of1h8-kJogPljLGCb5M_wKo/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_007 | Product Details | miss translation of 'عرض أكثر' to arabic content. | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345712 | 1-open Noon app. 2-navigate to products with arabic language. 3- open any product 4- click on 'عرض أكثر' | English TXT | Arabic TXT | Minor | Low | https://drive.google.com/file/d/19Yuzsy1nJMgj-r4lxZ89UR2khEwmEZiC/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_008 | Cart | Wrong Text in 'عربة التسوق' when it's empty. | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345713 | 1-open Noon app. 2-navigate to cart. | تأكد من شراء حاجة زي دي! | suitable text and navigation option to shopping | Cosmetic | Low | https://drive.google.com/file/d/1ZZwMTiq3jvW_CNZawyPeplX2wp83mYgY/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_009 | Mobile Data | missing reloading or view content when you disconnect data | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345714 | 1-open Noon app. 2-navigate to any page. 3- disconnect data. 4- try to reload or refress page or to navigate in the app. | oops! Error | view content usually | Minor | Medium | https://drive.google.com/file/d/1TgUijfzoCkMOHooqA4BlwqCJW6ZLXOX0/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_010 | شروط الاستخدام | the View of 'شروط الإستخدام' not RTL(Right to Lift) | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345715 | 1-open Noon app. 2-navigate to arabic language. 3- Then navigate to'شروط الاستخدام' then click on it. | LTR | RTL | Minor | Low | https://drive.google.com/file/d/1dQ8jthoAwHNMDxm7mopvxmX9gwYuTpbM/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_011 | شروط البيع | the View of 'شروط البيع' not RTL(Right to Lift) | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345716 | 1-open Noon app. 2-navigate to arabic language. 3- Then navigate to' شروط البيع' then click on it. | LTR | RTL | Minor | Low | https://drive.google.com/file/d/1WmZyn39gJ80sfK8aPDV_PO2bviz9DsSs/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_012 | Search | search Should be no letters case sensittive | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345717 | 1-open Noon app. 2-navigate to search box. 3- ex: look for' tornado solo'. | letter case sensitive | not be letter case sensitive | Major | Hight | https://drive.google.com/file/d/1sqOD5x6vi47FzB5Q5ZSus9IZ0wQjIvt-/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_013 | Orders,Returns,Noon Credits, Stores in My Account | navigation tab pressed, it reload the same page | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345718 | 1-open Noon app. 2-navigate to 'My Account'. 3- click on 'orders/returns/stores/noon credits' button meany times. | navigation tab pressed, it reload the same page | navigation tab pressed, should not reload the same page again | Critical | Hight | https://drive.google.com/file/d/1J32XxqiHbU3qx_ls6912ANK4FUuCgSR-/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_014 | UI | No mark that I am logged in at Home page. | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345719 | 1-open Noon app. 2-navigate to Home. | no mark showing that I am logged in | should be any sign that showing for user that he is logged in. | Minor | Medium | https://drive.google.com/file/d/1zJi9bnIb8gRuZRPZrcH9nO5-itTVBy9Q/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_015 | Products | Products tab pressed, should not reload the same page again | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345720 | 1-open Noon app. 2-navigate to Home. 3-many tab pressed in 'any product' | Products tab pressed, reload the same page again | Products tab pressed, should not reload the same page again | Major | Hight | https://drive.google.com/file/d/1zJi9bnIb8gRuZRPZrcH9nO5-itTVBy9Q/view?usp=sharing | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_016 |  |  | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345721 |  |  |  | None | None | attachement_016 | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_017 |  |  | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345722 |  |  |  | None | None | attachement_017 | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_018 |  |  | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345723 |  |  |  | None | None | attachement_018 | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_019 |  |  | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345724 |  |  |  | None | None | attachement_019 | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do
Noon_020 |  |  | The user can Download Noon app from app store or google play and the app should be accessable. | Email:test-qc@noon.com Password: 12345725 |  |  |  | None | None | attachement_020 | Samsung Galaxy A6+ One Ui version 2.0 Android Version 10 | Wifi/Data | Developer X | To Do